Terms of Reference No. 42

Position: Senior non-key expert (SNKE) for capacity building of MoLEVSA and NES in the field of Chapter 19 (Social Policy and Employment) under Activity 3.2.1 of the EU-funded project “Technical Assistance on implementation, monitoring, and evaluation of employment policy at national and local level and strengthened capacities to participate in ESF” (NEAR/BEG/2022/EA-RP/0105).

The SNKE expert engaged in the project Component 3 “To ensure that Serbian institutions and other relevant actors in the field of employment are prepared to meet the requirements of cohesion policy and participate in the European Social Fund (ESF +)” will enhance capacity of the MoLEVSA and NES to meet the obligations streaming from EU negotiation process, in particular Chapter 19 through provision of capacity building support.

- Project Background

The overall objective of the project is “to enhance employment and employability of the labour force focusing on youth, persons with disabilities, long-term unemployed and women” (Impact).

The specific objectives (Outcomes) of this contract are as follows:

- To support the MoLEVSA, NES and LSGs in improving effectiveness of ALMPs through improved design and analytical base for their implementation (Outcome 1)

- To build capacities of the relevant actors in the field of employment (MoLEVSA, NES, LSGs and other actors) to better perform their tasks related to implementation, monitoring and evaluation of ALMPs (Outcome 2)

- To ensure that Serbian institutions and other relevant actors are supported to meet the requirements of cohesion policy and participation in the European Social Fund (Outcome 3)

- To support piloting of Youth Guarantee Programme (Outcome 4)

The SNKE will provide support to Component 3 “To ensure that Serbian institutions and other relevant actors in the field of employment are prepared to meet the requirements of cohesion policy and participate in the European Social Fund (ESF +)” within which, the following outputs is to be achieved:

PO 3.2.1 - On-the job support to MoLEVSA and NES to meet the obligations streaming from EU negotiation process provided

- Reference document

Terms of Reference (ToR) of the Project: NEAR/BEG/2022/EA-RP/0105, “Technical Assistance on implementation, monitoring, and evaluation of employment policy at national and local level and strengthened capacities to participate in ESF”.

- Terms of Reference Relevance

This mission will contribute to strengthening Serbia’s preparedness for negotiations under Chapter 19 by supporting institutional capacity building, screening of the current acquis alignment status, and delivery of targeted training on employment policy–related acquis.

- Assignment objective(s)

The SNKE will provide support to the TA team to the following project activities:

- Activity 3.2.1: Enhance capacity of the MoLEVSA and NES to meet the obligations streaming from EU negotiation process, in particular Chapter 19 through provision of on-the-job support .

- Main tasks

The SNKE will provide support to and coordinate the work with the project TA team and JNKE in execution of the following tasks:

Activity 3.2.1

The SNKE will support the TA team in execution of the following tasks:

Task 3.2.1.1 – Preparation of Training Concept and Materials

- Design a comprehensive training programme tailored to the Serbian institutional context, ensuring that it reflects both acquis requirements and negotiation procedures.

- Develop training materials (presentations, case studies, handouts, practical exercises) covering: The EU acquis under Chapter 19; EU negotiation structures and procedures, including the role of national institutions; Employment legislation; Equal opportunities and non-discrimination in employment.

- Integrate lessons learned and best practices from EU Member States that have successfully negotiated Chapter 19.

Task 3.2.1.2 – Delivery of Training Workshops

- Deliver two structured training workshops for MoLEVSA and NES staff, in close cooperation with the TA team.

- Facilitate interactive discussions, group exercises, and practical assignments to enhance participant engagement.

- Provide written workshop reports, including participant feedback and recommendations for further capacity building.

Task 3.2.1.3 – Drafting of Recommendations and Final Report

- Prepare a set of practical recommendations in the field of employment policy, aligned with the latest EC recommendations.

- Summarise activity results, training content, and feedback from beneficiaries in a structured Final Activity Report.

- Submit the report in line with project reporting requirements, ensuring quality, clarity, and alignment with EU style standards.

- Related Outputs/Deliverables

Under the supervision of the TA team it is expected to the following deliverables to be produced as per activity:

Activity 3.2.1

- At least 20 Employees in the MoLEVSA organizational units dealing with employment policy and NES received capacity building support for Chapter 19

The timeframe set in the project work plan for the related activities must be observed in providing this support.

- Timing and duration of mission/s

The assignment shall be implemented in Belgrade, Serbia, in the following period:

| Position | Period of engagement | No. of WDS | Activity number | % of time to be spent in Republic of Serbia |
| --- | --- | --- | --- | --- |
| SNKE | January 2026 – May 2026 | Up to 15 working days | 3.2.1 | 100% |

The number of days is subject to extension as needed.

- Reporting

The SNKE will deliver monthly report in the English language on last workday of the month s/he worked, with attached all written deliverables and submitted to the Team Leader and in copy to the Project Assistant. The report will be attached to the expert’s draft timesheet.

9.	Expert profile

Qualifications and skills:

- University degree academic level in the field of Economy, Social sciences, or other related subjects.

- Good command of English written and spoken.

- Computer literacy (command of Microsoft Office /Word, Excel, PowerPoint, etc/and the Internet).

- Excellent communication and presentation skills.

- Analytical experience and skills.

- Excellent reporting skills.

- Ability to work in a team.

General professional experience

- At least 7 years of professional experience in employment policy or design/implementation of employment legislation and strategies.

Specific professional experience

- Proven experience in EU accession negotiations in the area of Chapter 19 (Social Policy and Employment), preferably as a member of a negotiation team or advisor.

- At least 5 years of experience in capacity building, training, or technical assistance related to employment or social policy.

- Familiarity with EU acquis requirements on employment policy and non-discrimination.

10.	Evaluation of work

The SNKE’s performance will be assessed by Beneficiary’s representatives and the project Team Leader.

11.	Applications

Application letter and EU format CV, both in English, must be submitted by e-mail to projekti.medjunarodna@minrzs.gov.rs, evukcevic@archidata.it and rbabic@archidata.it no later than January 30, 2026, titled: “Application for Senior non-key expert (SNKE) for capacity building of MoLEVSA and NES in the field of Chapter 19 (Social Policy and Employment)”.

References must be available on request.

Only short-listed candidates will be contacted.

The Project is an equal opportunity employer, in respect of the principles of good governance, sustainable development and gender equality.

- All applications will be considered strictly confidential.

- Advertised posts are not available to civil servants or other officials of the public administration in the beneficiary country, Serbia.