Terms of Reference No.44

Position: Senior Non-Key Expert (SNKE) for conducting in-depth analysis of inactive NEET youth registered with the National Employment Service (NES) under Activity 4.6.1 of the EU-funded project “Technical Assistance on implementation, monitoring, and evaluation of employment policy at national and local level and strengthened capacities to participate in ESF” (NEAR/BEG/2022/EA-RP/0105).

The SNKE expert engaged under the project Component 4 “Support to piloting and implementation of the Youth Guarantee Programme” will provide expertise and guidance in conducting an in-depth analysis of inactive NEET youth registered with the NES to support evidence-based implementation of the Youth Guarantee Programme in Serbia.

- Project Background

The overall objective of the project is “to enhance employment and employability of the labour force focusing on youth, persons with disabilities, long-term unemployed and women” (Impact).

The specific objectives (Outcomes) of this contract are as follows:

- To support the MoLEVSA, NES and LSGs in improving effectiveness of ALMPs through improved design and analytical base for their implementation (Outcome 1)

- To build capacities of the relevant actors in the field of employment (MoLEVSA, NES, LSGs and other actors) to better perform their tasks related to implementation, monitoring and evaluation of ALMPs (Outcome 2)

- To ensure that Serbian institutions and other relevant actors are supported to meet the requirements of cohesion policy and participation in the European Social Fund (Outcome 3)

- To support piloting of Youth Guarantee Programme (Outcome 4)

Within Component 4 – Support to piloting and implementation of the Youth Guarantee Programme, the project is implementing Activity 4.6.1: Additional analysis for effective implementation of YG Programme conducted and will contribute to the output:

- output 4.6.1 - Additional analysis for effective implementation of YG Programme conducted

- Reference document

Terms of Reference (ToR) of the Project: NEAR/BEG/2022/EA-RP/0105, “Technical Assistance on implementation, monitoring, and evaluation of employment policy at national and local level and strengthened capacities to participate in ESF”.

- Terms of Reference Relevance

This assignment contributes to strengthening Serbia’s preparedness for the full implementation of the Youth Guarantee (YG) Programme by supporting MoLEVSA and NES in analysing the profiles, needs and activation barriers of inactive NEET youth registered with the NES. The findings will inform the design of tailored support offers and activation pathways for young people furthest from the labour market.

- Assignment objective(s)

The objective of this assignment is to conduct an in-depth analysis of inactive NEET youth (aged 15–29) who are registered with NES but remain unengaged in activation measures, with the purpose of identifying typologies, needs, and obstacles to activation and proposing recommendations for tailored YG interventions.

Specific objectives are:

- To design a methodological framework for combining quantitative and qualitative data sources.

- To lead the analytical process and ensure quality, coherence and policy relevance.

- To identify profiles and barriers among inactive NEET youth.

- To prepare recommendations for development of tailored support packages under the Youth Guarantee.

- Main tasks

The SNKE will provide support to and coordinate the work with the project TA team and JNKE in execution of the following tasks:

Activity 4.6.1

Task 4.6.1.1 – Design of methodology and analytical framework

- Define methodological approach combining administrative and qualitative data.

- Specify inclusion criteria for the target group (inactive or long-term unemployed NEETs aged 15–29) (specific sub-groups to be analysed will be agreed with the MoLEVSA and NES)

- Develop analytical framework and structure for the final report.

Task 4.6.1.2 – Analysis of administrative data

- Identify relevant data sources and variables from NES records.

- Supervise data processing and segmentation by gender, age, education, and prior participation in active labour market programmes (ALMPs).

- Provide interpretation and analytical insights.

Task 4.6.1.3 – Qualitative research and synthesis

- Develop templates for interviews and focus groups.

- Supervise qualitative research with youth and NES counsellors.

- Ensure analytical integration of findings.

Task 4.6.1.4 – Preparation of recommendations

- Develop evidence-based recommendations for tailored YG activation packages.

- Suggest improvements to NES and MoLEVSA for activation of youth.

Task 4.6.1.5 – Reporting and presentation

- Draft analytical report and present findings to MoLEVSA and NES.

- Facilitate discussion on use of findings for YG implementation.

- Related Outputs/Deliverables

Under the supervision of the TA team it is expected to the following deliverables to be produced:

- Methodology note and analytical framework.

- Consolidated analysis of administrative and qualitative findings.

- Final analytical report with recommendations.

- Presentation of key results to MoLEVSA and NES.

The timeframe set in the project work plan for the related activities must be observed in providing this support.

- Timing and duration of mission/s

The assignment shall be implemented in Belgrade, Serbia, in the following period:

| Position | Period of engagement | No. of WDS | Activity number | % of time to be spent in Republic of Serbia |
| --- | --- | --- | --- | --- |
| SNKE | January 2026 – May 2026 | Up to 20 working days | 4.6.1 | 100% |

The number of days is subject to extension as needed.

- Reporting

The SNKE will deliver a report in English on the last working day of the month(s) s/he worked, attaching all written deliverables, and submit it to the Team Leader with copy to the Project Assistant.

The report will be attached to the expert’s draft timesheet.

9.	Expert profile

Qualifications and skills:

- University degree academic level in the field of Economy, Social sciences, or other related subjects.

- Good command of English written and spoken.

- Computer literacy (command of Microsoft Office /Word, Excel, PowerPoint, etc/and the Internet).

- Excellent communication and presentation skills.

- Analytical experience and skills.

- Excellent reporting skills.

- Ability to work in a team.

General professional experience

- At least 10 years of professional experience in conducting research, evaluation or analysis in the field of labour market and/or social policies and/or vulnerable groups.

Specific professional experience

- Minimum 1 relevant experience of team leader/lead researcher in research, evaluation or policy analysis in the field of labour market and/or social policies and/or vulnerable groups.

- Experience in applying mixed-method (quantitative/qualitative) analysis.

- Experience providing technical assistance to public institutions (MoLEVSA, NES, or similar).

- Familiarity with Youth Guarantee or similar EU employment initiatives is an advantage.

10.	Evaluation of work

The SNKE’s performance will be assessed by Beneficiary’s representatives and the project Team Leader.

11.	Applications

Application letter and EU format CV, both in English, must be submitted by e-mail to projekti.medjunarodna@minrzs.gov.rs, evukcevic@archidata.it and rbabic@archidata.it no later than January 30, 2026, titled: “Application for Senior Non-Key Expert (SNKE) for conducting in-depth analysis of inactive NEET youth registered with the National Employment Service (NSZ)”.

References must be available on request.

Only short-listed candidates will be contacted.

The Project is an equal opportunity employer, in respect of the principles of good governance, sustainable development and gender equality.

- All applications will be considered strictly confidential.

- Advertised posts are not available to civil servants or other officials of the public administration in the beneficiary country, Serbia.